## Tabelle1
Week | Day | Task_1 | Task_2 | Task_3 | Task_4 | Task_5 | Task_6 | Task_7
Week 1 | Monday | bar: Task_1
Week 1 | Tuesday | bar: Task_1
Week 1 | Wednesday | bar: Task_1
Week 1 | Thursday | bar: Task_1
Week 1 | Friday | Introductory test | Experiment planning | Treatment selection | Filling the reactors | Testing tightness | Pouring agar plates
Week 1 | Saturday | bar: Task_1
Week 1 | Sunday | bar: Task_1
Week 2 | Monday | Experiment start | PNF | pH | EC | FOS/TAC | DM d0 initial weight | PT plating
Week 2 | Tuesday | GM | DM d0 end weight | oDM intial weight | CNP grinding | PT evaluation
Week 2 | Wednesday | GM | PNF | ph | EC | FOS/TAC | TDM d2 initial weight | COD d0, d2 | Create master plates | oDM end weight
Week 2 | Thursday
Week 2 | Friday
Week 2 | Saturday
Week 2 | Sunday
Week 3 | Monday
Week 3 | Tuesday
Week 3 | Wednesday
Week 3 | Thursday
Week 3 | Friday
Week 3 | Saturday
Week 3 | Sunday